## Employee Experience Roadmap
|  |  | Immediate -- Foundation |  | Phase I: << timescale e.g. Q1, Fiscal Year X>> |  | Phase II: << timescale e.g. Q2, Fiscal Year X>> | Phase III: << timescale e.g. Q3, Fiscal Year X>>
| FEATURE OVERVIEW | Feature or activity area | Establish Employee Experience Program governance and strategies | Kick off program tactical supports | Review efficacy of current engagement survey | Day in the life
|  | Description | Establish the structure for the ongoing health and evolution for the roadmap. Secure the three necessary pillars for governance that support EX Program: • Executive sponsor(s): will give top-level support and business alignment • Steering committee: will oversee (providing different perspectives like HR, Comms, IT) • Operations team: will deliver on the roadmap (high level) | • Craft the overarching program Communications and Change Management approaches / plans • Identify initial sponsors, owners and delivery teams for roadmap initiatives • Start sharing the vision / roadshow to create understanding and excitement for the program | Determine if the survey is meeting our reporting needs. Are we asking the right questions, can we use the data we collect to drive action confidently (e.g. driver analysis), does the survey support multiple devices to allow for both office and plant employee access, etc. | Design and rollout pilot program for job shadowing throughout the organization. Start with 2 roles, across N.A. locations.
| VALUE GENERATION | Value to Employee |  |  | "I love our employee survey -- it's easy to use, the questions are clear, it takes hardly any time at all. I appreciate the effort it took to select and roll out, but I feel a lot more heard now than I did before." | “I loved my mandatory rotation on the customer help desk. It was only a day but it helped me get so much more in touch with what our clients are going through, as well as what our amazing CSRs have to deal with every day. This experience has made me better in my product development role.”
|  | Value to <<Org>> |  |  | • Collect data that allows us to follow through with "now what" decisions | • Use job shadowing to increase on-the-job skill development opportunities, empathy for co-workers and greater understanding of how we fundamentally work.
Audience size
| SCOPE | Impact (Breadth and depth within the organization)
Effort (Time, required resources, organizational readiness for change)
|  | Cost |  |  | $ | $$ | $$$
Size
| CONDITIONS FOR SUCCESS | Owner (Who is actively pushing this forward?)
Communications considerations (What Comms-related roles and activities are required for this initiative?)
Operational considerations (What roles and effort are needed to power this experience?)
Change aptitude
Change management (Are there specific CM tasks needed to complete this initiative?)
Dependencies (Are there other intiatives that need to be completed for this to be successful?)
POTENTIAL TECH
| SUCCESS | Expected outcomes
Success measures
2019-02-27
<<ORG>> Employee Experience Program Roadmap
VISION:
<<vision statement >>
GUIDING PRINCIPLES
PRINCIPLE 1
<insert details about the principle>
PRINCIPLE 2
<insert details about the principle>
PRINCIPLE 3
<insert details about the principle>
PRINCIPLE 4
<insert details about the principle>